## Gantt
 | time axis 2021-11-22 to 2022-11-21
 | time axis 2021-11-22 to 2022-11-21
LITERATURE | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
Orientation & Exploration | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
ü | Make planning | 2021-11-22: x; 2022-02-14: R; 2022-07-18: L
ü | Literature plan | 2021-11-22: x; 2021-12-20: x; 2022-01-17: x; 2022-02-14: U; 2022-07-18: I
ü | Literature research question | 2021-11-22: x; 2022-02-14: N; 2022-07-18: D
| MPC Theory | 2021-11-22: x; 2021-11-29: x; 2022-02-14: -; 2022-07-18: A
| MPC algorithms for amphibious robots | 2021-11-29: x; 2022-02-14: O; 2022-07-18: Y
Keelcrab model/underwater robot model + scenario | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
Above and under water simulation + disturbances | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
| Structured Literature Research | 2021-12-20: X; 2021-12-27: X; 2022-01-03: X; 2022-01-10: X; 2022-02-14: T; 2022-07-18: H
| Revisit research questions | 2021-12-20: x; 2022-02-14: I; 2022-07-18: O
| State-of-the-art MPC algorithms amphibious robots | 2021-12-20: x; 2021-12-27: x; 2022-01-03: x; 2022-01-10: x; 2022-02-14: M; 2022-07-18: L
[14 empty] | E | [21 empty] | I
Literature Documentation | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
Make overview of robot model and simulation | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
Make overview of MPC algorithms for amphibious robots | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
Literature report | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
Research question for thesis | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
Colloquia presentation | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
THESIS | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
| Analysis phase | 2022-02-21: X; 2022-02-28: X; 2022-03-07: X; 2022-07-18: O; 2022-09-26: R
| Revisit research proposal | 2022-02-21: x; 2022-07-18: L; 2022-09-26: U
| Research plan | 2022-02-28: x; 2022-03-07: x; 2022-07-18: I; 2022-09-26: N
| Research question | 2022-02-28: x; 2022-03-07: x; 2022-07-18: D; 2022-09-26: -
| hypothesis | 2022-02-28: x; 2022-03-07: x; 2022-07-18: A; 2022-09-26: O
| methodology | 2022-02-28: x; 2022-03-07: x; 2022-07-18: Y; 2022-09-26: U
T
Simulation Preparation | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
Build model of inspection Robot | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-09-26
| Perception & navigation algorithms for inspection robot | 2022-04-11: x; 2022-04-18: x; 2022-04-25: x; 2022-05-02: x; 2022-07-18: H; 2022-09-26: I
| MPC algorithm for inspection robot | 2022-05-09: x; 2022-05-16: x; 2022-05-23: x; 2022-05-30: x; 2022-06-06: x; 2022-06-13: x; 2022-07-18: O; 2022-09-26: M
| build Gazebo environment/test scenario | 2022-06-20: x; 2022-07-18: L; 2022-09-26: E
I
Simulation experiments | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
Simulation test | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
Adjust Robot model | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
Adjust MPC | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
R
Data Analysis | bar: 2021-11-22 to 2022-09-26
Analysis on MPC controller data | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-09-26
| Visualization (graphs/charts etc.) | 2022-07-18: H; 2022-09-19: x; 2022-09-26: -
[36 empty] | O | [9 empty] | O
[36 empty] | L | [9 empty] | U
| Writing paper | 2022-07-18: I; 2022-09-26: T; 2022-10-03: X; 2022-10-10: X; 2022-10-17: X; 2022-10-24: X; 2022-10-31: X; 2022-11-07: X
General structure | bar: 2021-11-22 to 2022-07-18; 2022-08-01 to 2022-11-21
| First draft | 2022-07-18: A; 2022-09-26: T; 2022-10-10: x; 2022-10-17: x
| Second draft | 2022-07-18: Y; 2022-09-26: I; 2022-10-24: x; 2022-10-31: x
Final paper | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
E
Presentation & Defense | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
Make presentation | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
Prepare Defence | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21
Give presentation & defence | bar: 2021-11-22 to 2022-07-11; 2022-08-01 to 2022-11-21

## TODO
WHAT | DATE | DUE DATE | TO DO | BUSY | COMPLETED | COMPLETION DATE | ü
Fix thesis contracts | 2021-11-22 | 2021-11-22 |  | x
Email to Keelcrab company about model/information | 2021-11-22 | 2021-11-29 |  |  | ü | 2021-11-29
Get in contact with Tasos Tsolakis | 2021-11-26 | 2021-12-05 | x
Read literature study by Abram | 2021-11-26 | 2021-12-05 | x
Adjust Gantt planning for iterative literature study | 2021-11-26 | 2021-12-05 | x
Make rough setup for literature study | 2021-11-26 | 2021-12-12 | x
Contact Client about possible disturbances | 2021-11-23 | 2021-12-13 | x
Check Schedule for colloquia presentation | 2021-11-22 | 2021-12-27 | x
Discussion with client about research | 2021-11-22 | 2022-02-28 | x

## Questions
Laura |  | Réka |  | Client
Question | Answer | Question | Answer | Question | Answer
What are the Leading researchers/research institutes on MPC? | no answer |  |  | What is the specific Keelcrab robot model? | keelcrab boat cleaner
What are important journals/conferences on MPC? | no answer |  |  | What are the disturbances during the inspection?
What are the seminal articles/books on MPC? | Maciejowski, lecture by Laura, rawlings |  |  | How do you efficiently cover parts of map for inspection?
What are the current methods for inspection on quay walls?

## Logbook
Date | What
2021-11-22 | Email Andries about contract, mail Laura on update and questions, Make Gantt schedule, make to-do list
2021-11-23 | Make literature plan, read part of Maciejowski book, mail to andries and laura
2021-11-26 | Meeting with Laura group, read Maciejowski